| To: | All Team Members — Micurato Development Team |
| --- | --- |
| From: | Noor Khan, Project Manager |
| Date: | 16 June 2026 |
| Subject: | Action Required: Jira Process Standards — Issue Types, Story Points & Sprint Cadence |

Hi Team,

We are standardising how we work in Jira across all projects. Starting from the next sprint, every team member must follow the structure and field rules below. Consistent ticket hygiene gives leadership real-time visibility, keeps sprints predictable, and makes stand-ups faster.

Please read this carefully and apply it from your next sprint.

1.  Sprint Cadence — 1 Sprint = 1 Week

Every sprint is exactly 1 week (5 working days). Sprint starts: Monday morning ¦ Sprint ends: Friday evening Sprint planning: Monday ¦ Sprint review & retrospective: Friday

Because each sprint is one week, all work must fit within 5 working days. This means:

- No story should exceed 5 story points (1 full week of effort)

- Stories larger than 5 SP must be split into smaller stories before sprint planning

- Subtasks within a story should be sized so the story completes within the sprint

- Any work that cannot finish within one week must be planned across sprints as separate stories

2.  Issue Types — How We Organise Work

We use three issue types. Use the right type for the right work:

| Type | Icon | When to Use | Can Have Children? |
| --- | --- | --- | --- |
| Story | 📖 Story | A feature, requirement, or piece of user-facing work that needs multiple people or steps to complete | Yes — add Subtasks (FE, BE, QA) |
| Task | ✅ Task | Standalone, independent work that does not belong under a Story — e.g. setup, config, research, documentation | No — Tasks are independent |
| Bug | 🐛 Bug | A defect or unexpected behaviour found in production or during QA — always raised with steps to reproduce | No — Bugs are standalone |
| Subtask | 🔧 Subtask | A specific piece of work under a Story — one per discipline (FE / BE / QA) | No — always a child of a Story |

Rule: Every Story must have at least one Subtask before moving to In Progress. Typical pattern: [FE] Subtask + [BE] Subtask + [QA] Subtask Each subtask is assigned to the responsible person and carries its own story points.

3.  Story Points — Everyone Must Estimate

Story points apply to all issue types — Story, Task, Bug, and Subtask. No ticket goes into a sprint without an SP estimate.

| Points | Time | Typical Use | Example |
| --- | --- | --- | --- |
| 0.5 | Half day | Minor tweak, quick QA check | Fix label text, verify a button behaviour |
| 1 | 1 day | Clear, well-scoped task | Build a form component, write unit tests |
| 2 | 2 days | Moderate work or some unknowns | Integrate a new API endpoint |
| 3 | 3 days | Complex work with dependencies | Design + implement a full module |
| 5 | 1 week (full sprint) | Maximum — must fill the entire sprint | End-to-end feature across FE + BE + QA |

Sprint limit: 1 sprint = 1 week = max 5 SP per story. Any story estimated above 5 SP must be split before sprint planning starts. Story SP = sum of all its subtask SPs. Set SP on subtasks first, then total on the Story.

SP assignment by role (typical):

- [FE] Subtask — 1 to 2 SP depending on UI complexity

- [BE] Subtask — 1 to 2 SP depending on logic and data layer

- [QA] Subtask — 0.5 to 1 SP for test execution and verification

- Task (independent) — estimate directly, same scale

- Bug — estimate the fix effort, not the severity

4.  Mandatory Fields — By Issue Type

Tickets missing these fields will be returned during sprint planning and will not count toward sprint delivery.

4a.  Story

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | Clear, user-facing description | Searchability and planning clarity |
| Assignee | Story owner / lead | Accountability and workload tracking |
| Story Points | Sum of subtask SPs | Sprint velocity and capacity planning |
| Start Date | Planned start (Monday) | Timeline tracking |
| Due Date | Sprint end (Friday) | Delivery deadline visibility |
| Priority | High / Medium / Low | Sequencing and triage |
| Sprint | Active sprint name | Board visibility |
| Description | Acceptance criteria | Defines what Done looks like |
| Subtasks | Minimum 1 subtask created | Cannot move to In Progress without subtasks |

4b.  Subtask (child of Story)

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | [FE] / [BE] / [QA] + description | Instantly identifies the discipline |
| Parent Story | Linked to parent Story | Rollup to story level tracking |
| Assignee | The developer / QA doing the work | Individual velocity tracking |
| Story Points | 0.5 / 1 / 2 / 3 | Feeds into Story and sprint burndown |
| Status | Updated daily | Dashboard and sprint tracking |

4c.  Task (independent work)

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | Clear, actionable description | Searchability |
| Assignee | Named team member | Clear ownership |
| Story Points | 0.5 / 1 / 2 / 3 / 5 | Sprint capacity and velocity |
| Start & Due Date | Within sprint week | Timeline tracking |
| Sprint | Active sprint name | Board visibility |
| Priority | High / Medium / Low | Triage and sequencing |

4d.  Bug

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | What broke + where | Fast identification |
| Assignee | Named developer | Clear ownership |
| Story Points | Estimate the fix effort | Sprint capacity impact |
| Priority | Critical / High / Medium / Low | Determines urgency of fix |
| Description | Steps to reproduce + expected vs actual | Reproducibility and fix accuracy |
| Environment | Staging / Production / Local | Scope of impact |
| Sprint | Active sprint or Backlog | Prioritisation |

5.  Status Workflow — Update Every Day

Status must reflect your actual progress. Never leave a ticket on an old status for more than 24 hours.

| From Status |  | To Status | When |
| --- | --- | --- | --- |
| To Do | → | In Progress | When you start work |
| Dev in Progress | → | In Code Review | PR raised, awaiting review |
| In Code Review | → | Ready for QA | Code reviewed and merged |
| Ready for QA | → | Verification Passed | QA testing passed |
| Verification Passed | → | Done | Deployed and confirmed live |

Blocked? Move ticket to On Hold + comment tagging the blocker (@person or linked ticket) + notify your manager immediately.

6.  Definition of Ready & Definition of Done

| Definition of Ready (before sprint) - All mandatory fields filled in - Story has at least one Subtask created - Story Points estimated on all subtasks - Acceptance criteria written in Description - Start Date = Monday, Due Date = Friday - Priority set - Sprint assigned | Definition of Done (before closing) - All subtasks are closed - Code reviewed and merged - QA Verification Passed - Deployed to production - Closing comment added - Status moved to Done - Any linked tickets updated |
| --- | --- |

7.  Weekly Sprint Calendar

| Day | Event | What Happens |
| --- | --- | --- |
| Monday | Sprint Planning | Review backlog, assign stories, confirm subtasks and SPs are ready for all tickets entering the sprint |
| Mon–Fri | Daily Standup | 15 min: What did I do yesterday? What am I doing today? Any blockers? — update Jira status before standup |
| Thursday | Mid-sprint check | Manager reviews dashboard for at-risk tickets — blockers escalated, remaining scope adjusted if needed |
| Friday | Sprint Review | Demo completed work, mark Done tickets, celebrate wins, and close the sprint in Jira |
| Friday | Retrospective | 15 min: What went well? What can improve? One action item for next sprint |

8.  The Golden Rule

If you touched a ticket today — update it today. Status, comment, or progress note. Every day. Non-negotiable.

Tickets not updated for more than 48 hours during a sprint will be flagged in standup. Repeated instances will be escalated.

If you have questions about any of this, raise them in sprint planning or reach out to me directly. Let's make this sprint — and every sprint — count.

Best regards,

Noor Khan

Project Manager — Micurato

Dashboard: https://micurato.atlassian.net/jira/dashboards/10001?maximized=12561