| To: | All Team Members — Micurato Development Team |
| --- | --- |
| From: | Noor Khan, Project Manager |
| Date: | 12 June 2026 |
| Subject: | Action Required: Jira Process Standards — Mandatory Fields, Story Points & Dashboard |

Hi Team,

As we scale our delivery process, we are standardising how we use Jira across all projects. This document outlines the mandatory practices every team member must follow when creating and updating tickets. Consistent Jira hygiene directly improves sprint visibility, individual accountability, and delivery tracking for leadership.

Please read this carefully and apply these standards starting from your next sprint.

1.  Your Sprint Dashboard

All team members and managers should bookmark and regularly check the following dashboard for a live view of sprint progress, individual workloads, and project status:

Team Sprint Dashboard https://micurato.atlassian.net/jira/dashboards/10001?maximized=12561 Refresh this page at the start and end of each working day to keep it current.

2.  Issue Hierarchy

All work must follow this three-level hierarchy:

| Level | Type | Purpose |
| --- | --- | --- |
| 1 | EPIC | Large feature or initiative spanning multiple sprints |
| 2 | Story | A deliverable feature or requirement, completed in one sprint |
| 3 | Task (FE / BE / QA) | Specific implementation task under a Story — one per discipline |

Every Story must have exactly three child Tasks before it moves to In Progress:

- FE Task — assigned to the Frontend developer

- BE Task — assigned to the Backend developer

- QA Task — assigned to the QA engineer

3.  Story Points Standard

Story points represent time effort. Our scale is simple:

| Story Points | Effort | Use When |
| --- | --- | --- |
| 0.5 | Half day | Small task, minor fix, quick review |
| 1 | 1 full day | Standard task with clear scope |
| 2 | 2 days | Moderate complexity or unknowns |
| 3 | 3 days | Complex work requiring research |
| 5 | 1 week | Should be broken into smaller stories |

Rule: Any Story with more than 5 SP total must be broken into two or more Stories before sprint planning.

Story points are set at the Task level. The parent Story SP = sum of all child task SPs.

- Example: FE Task (1 SP) + BE Task (1 SP) + QA Task (0.5 SP) = Story (2.5 SP)

4.  Mandatory Fields

Tickets without these fields will be returned during sprint planning and will NOT be counted as sprint deliverables.

4a.  Story — Mandatory Fields

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | Clear, descriptive title | Searchability and sprint planning |
| Epic Link | Must be linked to an EPIC | Tracks feature-level progress |
| Assignee | Named team member | Clear ownership |
| Story Points | Sum of child task SPs | Sprint velocity measurement |
| Start Date | Planned start date | Delivery timeline tracking |
| Due Date | Expected completion date | Deadline visibility for managers |
| Priority | High / Medium / Low | Helps triage and sequencing |
| Sprint | Active sprint name | Sprint board visibility |
| Description | Acceptance criteria | Defines what Done looks like |

4b.  Task (FE / BE / QA) — Mandatory Fields

| Field | Required Value | Why It Matters |
| --- | --- | --- |
| Summary / Title | [FE] / [BE] / [QA] prefix + title | Easy identification of task type |
| Parent Story | Linked to parent Story | Rollup tracking to Story level |
| Assignee | Named developer / QA | Individual velocity tracking |
| Story Points | 0.5 / 1 / 2 / 3 | Individual effort tracking |
| Start Date | Planned start date | Timeline dependency visibility |
| Due Date | Expected completion date | Sprint burndown accuracy |
| Status | Updated daily | Dashboard and sprint tracking |

5.  Status Workflow — Update Every Day

Status must reflect your actual progress. Never leave a ticket on an old status for more than 24 hours.

| Status |  | Move To | When |
| --- | --- | --- | --- |
| To Do | → | In Progress | When you start working on it |
| In Progress / Dev in Progress | → | In Code Review | PR raised, awaiting review |
| In Code Review | → | Ready for QA | Code reviewed and merged |
| Ready for QA | → | Verification Passed | QA testing passed |
| Verification Passed | → | Done | Deployed and confirmed live |

If you are blocked at any stage: 1. Move the ticket to On Hold 2. Add a comment tagging the blocker (@person or linked ticket) 3. Notify your manager immediately — do not wait for standup

6.  Definition of Ready & Definition of Done

| Definition of Ready (Before Starting) - All mandatory fields filled in - Story has FE, BE, and QA tasks created - Story Points assigned on all tasks - Acceptance criteria written in Description - Start Date and Due Date set - Epic Link attached | Definition of Done (Before Closing) - All sub-tasks are closed - Code reviewed and merged - QA Verification Passed - Closing comment added (what was delivered) - Status moved to Done - Any related tickets linked |
| --- | --- |

7.  The Golden Rule

If you touched a ticket today — update it today. Status, comment, or progress note. This is non-negotiable.

Tickets that are not updated for more than 48 hours during a sprint will be flagged in the daily standup. Repeated instances will be escalated.

If you have any questions about this process, please reach out directly or raise it in the next sprint planning session.

Thank you for your cooperation in making our sprints more predictable and our delivery more transparent.

Best regards,

Noor Khan

Project Manager — Micurato

Dashboard: https://micurato.atlassian.net/jira/dashboards/10001?maximized=12561